## Epics
Description | Status | Notes
Create Description on Indie Hackers
Confirm App is usable on a phone
On a phone, should function as a PWA
Report on Epics 06/13/2020
We are still missing some core features regarding support for user accounts. I think these are important enough to delay launch

## Tasks
Description | Iteration | Area | Status | Notes
create a way to delete everything in the database - and seed users with fresh data | 1 | Admin | Not Done
Allow Users to have their own items on the calendar | 1 | Calendar | Not Done | Currently, calendar is shared among all users. This needs to be built to support users
add filters to food items | 2 | Food Items Grid | Not Done
add sorting to food items | 2 | Food Items Grid | Not Done
food items should require name | 1 | Food Items Grid | Not Done
set cost as low , medium, high | 2 | Food Items Grid | Not Done
add star ratings - how much do I enjoy eating this food | 2 | Food Items Grid | Not Done
create thumbnail images for each of the food groups | 1 | Food Items Grid | Not Done
need to add userid to dbo.meals table | 1 | Meals Grid | Done
Food Items and Meals should also be divided by user | 1 | User Accounts | Not Done

## Notes
6/14/2020 I need to get a V1 up online soon - let's finish the iteration 1 tasks, create the basic product info on IH, and start sharing some of our information on the blueprogrammer blog.

## Tests
Description | Status
Check Meal creation intuitive and clear
Check Food Item management intuitive and clear
Check User Support For Food Items
Check User Support For Meals

## Ideas
Description | Status
create the shortcuit ability to crfeate new foods with control + n [anything to avoid having to click th emouse]
create a logo for each of the food groups to better visualize WTF Is happening within the meal builder